**BEFORE THE**

**COUNCIL OF THE CITY OF NEW ORLEANS**

|  |  |  |
| --- | --- | --- |
| **IN RE: 2018 TRIENNIAL INTEGRATED RESOURCE PLAN OF ENTERGY NEW ORLEANS, INC.** | **)**  **)**  **)**  **)** | **DOCKET NO. UD-17-03** |

**ORDER**

On March 16, 2018, the Advisors to the Council of the City of New Orleans ("Advisors") filed a Motion to Extend Procedural Deadlines and accompanying Memorandum in Support requesting that the procedural schedule in this docket be adjusted in order to allow for sufficient time for the Council to execute the contract with the chosen DSM Potential Study consultant, and for the DSM Potential Study consultant to complete the work.

Considering the Motion, Memorandum in Support and that no party has objected to the request, the Advisors' Motion is hereby granted and the new procedural deadlines are as follows:

|  |  |
| --- | --- |
| **Deadline** | **New Deadline** |
| The DSM Potential Studies to be submitted in the proceeding shall be completed. | August 31, 2018 |
| Technical Meeting 2 of the Parties, CURO and Advisors shall be held between these dates. | Sept. 17-28, 2018 |
| Last date for the issuance of the council policies that must be included in the optimization process. | Oct. 31, 2018 |
| Technical meeting 3 of the Parties, CURO, and the Advisors shall be held between these dates. | Nov. 19-30, 2018 |
| All IRP inputs shall be finalized. | Dec. 7, 2018 |
| ENO shall complete all optimized portfolio development and results. | April 8, 2019 |
| Technical meeting 4 of the parties, CURO and Advisors shall be held between these dates. | April 22-May 3, 2019 |
| 2018 IRP Report shall be filed. | July 19, 2019 |
| The second public meeting shall be held between these dates. | July 29-Aug. 9, 2019 |
| The third public meeting shall be held between these dates. | Aug. 28-Sept. 11, 2019 |
| Technical meeting 5 of the Parties, CURO, and Advisors shall be held between these dates. | Aug. 28- Sept. 11, 2019 |
| Intervenor comments on the Final IRP filing shall be filed. | Sept. 16, 2019 |
| ENO reply comments shall be filed. | Oct. 29, 2019 |
| The Advisor Report shall be filed. | Dec. 2, 2019 |
| The Energy Smart Implementation filing for Program Years 10-12 shall be filed. | Dec. 9, 2019 |

SO ORDERED, this \_\_\_\_\_ day of March, 2018.

JEFFREY S. GULIN,

Hearing Officer