## Export
Data per ENO Project List and 1898 Modeling Estimates (static) | [10 empty] | Engineering Phase (Phase 2) | [8 empty] | Construction Phase (Phase 3) | [10 empty] | Closeout Phase (Phase 4)
Primavera Project # | TD | Region | Program Name | Baseline Start Year | Baseline End Year | Actual Start | Investment (Nominal) | Structures to be Hardened | OH to be Converted to UG (Miles) | Copper Length to be Replaced (Miles) | Project EAC (Nominal) Ph 2 | Structures to be Hardened Ph2 | OH to be Converted to UG (Miles) Ph2 | Copper Length to be Replaced (Miles) Ph2 | Percent Complete Ph2 | Actual Start Ph2 | Planned Start Ph2 | Actual Finish Ph2 | Planned Finish Ph2 | Project EAC (Nominal) Ph 3 | Structures to be Hardened Ph3 | OH to be Converted to UG (Miles) Ph3 | Copper Length to be Replaced (Miles) Ph3 | Percent Complete Ph3 | Actual Start Ph3 | Planned Start Ph3 | Actual ISD | Planned ISD | Actual Finish Ph3 | Planned Finish Ph3 | Actual Cost Project to Date (Nominal) | Actual Structures Hardened Ph 4 | Actual OH to UG Conversion (Miles) Ph 4 | Actual Copper Length Replaced (Miles) Ph 4 | Percent Complete Ph4 | Actual Start Ph4 | Planned Start Ph4 | Actual Finish Ph4 | Planned Finish Ph4
P3000 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-03-10 |  | 184 | 0 | 2.4141 |  | 93 | 0 | 0.119 | 36.31% | 2025-03-06 | 3/6/2025 |  | 8/20/2026 |  |  |  |  | 0% |  | 9/28/2026 |  | 2026-12-29 |  | 1/26/2027 |  |  |  |  | 0% |  |  |  | 3/24/2027
P3001 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-02-12 |  | 288 | 0 | 3.2395 |  | 163 | 0 | 0.1 | 75% | 2025-05-27 | 5/27/2025 |  | 7/10/2026 |  |  |  |  | 0% |  | 8/10/2026 |  | 2026-12-01 |  | 12/29/2026 |  |  |  |  | 0% |  |  |  | 2/26/2027
P3006 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-03-05 |  | 115 | 0 | 2.0673 |  | 60 | 0 | 0 | 100% | 2025-03-17 | 3/17/2025 | 2025-12-02 | 12/2/2025 |  | 97 | 0 | 0.05 | 0% | 2025-12-08 | 12/8/2025 |  | 2026-03-16 |  | 4/9/2026 |  |  |  |  | 0% |  |  |  | 6/8/2026
P3008 | Distribution | METRO | Distribution Feeder Hardening-Rebuild, Lateral Hardening-Rebuild | 2025 | 2026 | 2025-03-05 |  | 183 | 0 | 1.3925 |  | 109 | 0 | 0.45 | 100% | 2025-03-17 | 3/17/2025 | 2025-12-02 | 12/2/2025 |  | 166 | 0 | 1.56 | 0% | 2025-12-15 | 12/15/2025 |  | 2026-04-06 |  | 4/30/2026 |  |  |  |  | 0% |  |  |  | 6/29/2026
P3009 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-05-14 |  | 226 | 0 | 2.5966 |  | 140 | 0 | 0.04 | 85% | 2025-04-01 | 4/1/2025 |  | 3/27/2026 |  |  |  |  | 0% |  | 4/13/2026 |  | 2026-05-26 |  | 6/19/2026 |  |  |  |  | 0% |  |  |  | 8/18/2026
P3010 | Distribution | METRO | Distribution Feeder Hardening-Rebuild, Lateral Hardening-Rebuild | 2025 | 2026 | 2025-03-05 |  | 200 | 0 | 1.7299 |  | 119 | 0 | 0.5 | 80% | 2025-03-06 | 3/6/2025 |  | 3/26/2026 |  |  |  |  | 0% |  | 3/27/2026 |  | 2026-05-22 |  | 6/18/2026 |  |  |  |  | 0% |  |  |  | 8/17/2026
P3011 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2025 | 2025-02-12 |  | 47 | 0 | 0.0076818 |  | 45 | 0 | 0 | 100% | 2025-03-13 | 3/13/2025 | 2025-08-05 | 8/5/2025 |  | 50 | 0 | 0.96 | 90% | 2025-08-25 | 8/25/2025 | 2025-12-22 | 2025-12-22 |  | 2/19/2026 |  |  |  |  | 0% |  |  |  | 4/17/2026
P3013 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-01-21 |  | 9 | 0 | 0.069074 |  | 8 | 0 | 0.105 | 100% | 2025-03-13 | 3/13/2025 | 2025-08-05 | 8/5/2025 |  | 9 | 0 | 0.04697 | 100% | 2025-08-12 | 8/12/2025 | 2025-09-09 | 2025-09-09 | 2025-10-17 | 10/17/2025 |  |  |  |  | 90% |  |  |  | 3/16/2026
P3014 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-04-10 |  | 81 | 0 | 0.86106 |  | 51 | 0 | 0.42 | 75% | 2025-05-12 | 5/12/2025 |  | 7/31/2026 |  |  |  |  | 0% |  | 8/3/2026 |  | 2026-09-28 |  | 10/22/2026 |  |  |  |  | 0% |  |  |  | 12/21/2026
P3015 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-04-07 |  | 46 | 0 | 0.54047 |  | 33 | 0 | 0.54 | 85% | 2025-05-06 | 5/6/2025 |  | 7/24/2026 |  |  |  |  | 0% |  | 8/3/2026 |  | 2026-10-12 |  | 11/5/2026 |  |  |  |  | 0% |  |  |  | 1/7/2027
P3016 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-03-05 |  | 79 | 0 | 0.52879 |  | 41 | 0 | 0.59 | 100% | 2025-03-05 | 3/5/2025 | 2025-08-19 | 8/19/2025 |  | 65 | 0 | 1.8337 | 93.33% | 2025-10-09 | 10/9/2025 | 2025-12-22 | 2025-12-22 |  | 2/19/2026 |  |  |  |  | 30% |  |  |  | 4/7/2026
P3017 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-02-12 |  | 57 | 0 | 0.43694 |  | 32 | 0 | 0.23 | 100% | 2025-03-25 | 3/25/2025 | 2025-10-20 | 10/20/2025 |  | 49 | 0 | 0.48 | 90% | 2025-10-21 | 10/21/2025 | 2025-12-22 | 2025-12-22 |  | 2/19/2026 |  |  |  |  | 0% |  |  |  | 4/17/2026
P3018 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-03-05 |  | 75 | 0 | 0.70622 |  | 60 | 0 | 0.4 | 75% | 2025-03-11 | 3/11/2025 |  | 9/18/2026 |  |  |  |  | 0% |  | 10/19/2026 |  | 2026-12-29 |  | 1/26/2027 |  |  |  |  | 0% |  |  |  | 3/24/2027
P3020 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-06-03 |  | 62 | 0 | 0.31964 |  | 39 | 0 | 0 | 85% | 2025-06-03 | 6/3/2025 |  | 3/26/2026 |  |  |  |  | 0% |  | 3/23/2026 |  | 2026-06-01 |  | 6/25/2026 |  |  |  |  | 0% |  |  |  | 8/24/2026
P3022 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-06-03 |  | 44 | 0 | 0.12846 |  | 25 | 0 | 0.13 | 85% | 2025-05-21 | 5/21/2025 |  | 4/30/2026 |  |  |  |  | 0% |  | 4/20/2026 |  | 2026-06-02 |  | 6/26/2026 |  |  |  |  | 0% |  |  |  | 8/25/2026
P3023 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-02-03 |  | 11 | 0 | 0 |  | 8 | 0 | 0 | 100% | 2025-03-14 | 3/14/2025 | 2025-09-08 | 9/8/2025 |  | 8 | 0 | 0.01 | 100% | 2025-10-03 | 10/3/2025 | 2025-11-12 | 2025-11-12 | 2025-11-19 | 11/19/2025 |  |  |  |  | 90% |  |  |  | 3/23/2026
P3024 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-05-07 |  | 56 | 0 | 0.61085 |  | 39 | 0 | 0.404 | 100% | 2025-03-26 | 3/26/2025 | 2025-12-02 | 12/2/2025 |  | 47 | 0 | 0.404 | 40.41% | 2025-12-03 | 12/3/2025 |  | 2026-03-09 |  | 4/2/2026 |  |  |  |  | 0% |  |  |  | 6/1/2026
P3025 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-05-22 |  | 43 | 0 | 0.61844 |  | 32 | 0 | 0.33 | 100% | 2025-04-07 | 4/7/2025 | 2025-12-02 | 12/2/2025 |  | 44 | 0 | 0.85 | 42.95% | 2025-12-03 | 12/3/2025 |  | 2026-03-09 |  | 4/2/2026 |  |  |  |  | 0% |  |  |  | 6/1/2026
P3026 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-02-03 |  | 28 | 0 | 0.094792 |  | 29 | 0 | 0.42 | 100% | 2025-03-13 | 3/13/2025 | 2025-07-21 | 7/21/2025 |  | 37 | 0 | 0.73579 | 100% | 2025-07-28 | 7/28/2025 | 2025-09-04 | 2025-09-04 | 2025-10-20 | 10/20/2025 |  |  |  |  | 90% |  |  |  | 3/16/2026
P3027 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-02-26 |  | 12 | 0 | 0.068864 |  | 12 | 0 | 0.02 | 100% | 2025-03-10 | 3/10/2025 | 2025-04-11 | 4/11/2025 |  | 8 | 0 | 0 | 100% | 2025-04-14 | 4/14/2025 | 2025-05-05 | 2025-05-05 | 2025-05-19 | 5/19/2025 |  |  |  |  | 90% |  |  |  | 3/16/2026
P3028 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-02-19 |  | 23 | 0 | 0 |  | 14 | 0 | 0 | 100% | 2025-03-10 | 3/10/2025 | 2025-08-19 | 8/19/2025 |  | 13 | 0 | 0 | 98.75% | 2025-09-05 | 9/5/2025 | 2025-10-28 | 2025-10-28 |  | 2/19/2026 |  |  |  |  | 67.5% |  |  |  | 4/6/2026
P3029 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2025 | 2025-02-18 |  | 26 | 0 | 0.020858 |  | 19 | 0 | 0.049 | 100% | 2025-04-10 | 4/10/2025 | 2025-08-19 | 8/19/2025 |  | 16 | 0 | 0.315 | 90% | 2025-10-13 | 10/13/2025 | 2025-12-10 | 2025-12-10 |  | 2/5/2026 |  |  |  |  | 0% |  |  |  | 4/3/2026
P3030 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-03-31 |  | 116 | 0 | 0.027765 |  | 76 | 0 | 0 | 85% | 2025-03-06 | 3/6/2025 |  | 5/7/2026 |  |  |  |  | 0% |  | 5/26/2026 |  | 2026-07-27 |  | 8/20/2026 |  |  |  |  | 0% |  |  |  | 10/19/2026
P3031 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-05-05 |  | 172 | 0 | 2.5037 |  | 121 | 0 | 0 | 75% | 2025-05-21 | 5/21/2025 |  | 7/17/2026 |  |  |  |  | 0% |  | 8/3/2026 |  | 2026-09-21 |  | 10/19/2026 |  |  |  |  | 0% |  |  |  | 12/16/2026
P3032 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-04-10 |  | 99 | 0 | 0.42098 |  | 67 | 0 | 0.11 | 85% | 2025-03-17 | 3/17/2025 |  | 5/14/2026 |  |  |  |  | 0% |  | 6/1/2026 |  | 2026-07-27 |  | 8/20/2026 |  |  |  |  | 0% |  |  |  | 10/19/2026
P3033 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-04-10 |  | 136 | 0 | 1.1839 |  | 78 | 0 | 0.25 | 66.03% | 2025-03-13 | 3/13/2025 |  | 9/18/2026 |  |  |  |  | 0% |  | 10/19/2026 |  | 2026-12-29 |  | 1/26/2027 |  |  |  |  | 0% |  |  |  | 3/24/2027
P3034 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-03-10 |  | 127 | 0 | 3.7339 |  | 57 | 0 | 0 | 100% | 2025-03-17 | 3/17/2025 | 2025-06-17 | 6/17/2025 |  | 100 | 0 | 3.1625 | 100% | 2025-07-07 | 7/7/2025 | 2025-10-29 | 2025-10-29 | 2025-12-11 | 12/11/2025 |  |  |  |  | 90% |  |  |  | 3/16/2026
P3037 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-04-10 |  | 110 | 0 | 2.0572 |  | 74 | 0 | 0 | 80% | 2025-05-21 | 5/21/2025 |  | 5/7/2026 |  |  |  |  | 0% |  | 6/1/2026 |  | 2026-08-03 |  | 8/27/2026 |  |  |  |  | 0% |  |  |  | 10/26/2026
P3041 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2025 | 2025-05-14 |  | 122 | 0 | 1.1628 |  | 77 | 0 | 0.1 | 100% | 2025-03-18 | 3/18/2025 | 2025-10-20 | 10/20/2025 |  | 121 | 0 | 0 | 71.13% | 2025-10-21 | 10/21/2025 |  | 2026-03-09 |  | 4/2/2026 |  |  |  |  | 0% |  |  |  | 6/1/2026
P3044 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-06-03 |  | 105 | 0 | 0.3959 |  | 95 | 0 | 0 | 75% | 2025-03-13 | 3/13/2025 |  | 7/10/2026 |  |  |  |  | 0% |  | 8/10/2026 |  | 2026-10-12 |  | 3/31/2027 |  |  |  |  | 0% |  |  |  | 7/12/2027
P3045 | Distribution | METRO | Lateral Hardening-Rebuild | 2025 | 2026 | 2025-05-21 |  | 86 | 0 | 0.12569 |  | 70 | 0 | 0 | 80% | 2025-03-13 | 3/13/2025 |  | 6/12/2026 |  |  |  |  | 0% |  | 7/7/2026 |  | 2026-09-08 |  | 2/15/2027 |  |  |  |  | 0% |  |  |  | 3/30/2027
P3046 | Distribution | METRO | Distribution Feeder Hardening-Rebuild | 2025 | 2026 | 2025-06-03 |  | 133 | 0 | 0 |  | 79 | 0 | 0 | 59.24% | 2025-06-02 | 6/2/2025 |  | 8/27/2026 |  |  |  |  | 0% |  | 9/28/2026 |  | 2026-12-29 |  | 1/26/2027 |  |  |  |  | 0% |  |  |  | 3/24/2027